## 📊 Dashboard
🚀 AI Travel Planner — Project Tracker
Last Updated: (enter date)
Total Features |  | ✅ Done |  | 🔄 In Progress |  | 📋 To Do |  | 🚫 Blocked
-130 |  | 3 |  | 4 |  | 27 |  | 0
Overall Progress |  | 8.824% | [5 empty] | % Complete
Module / Category | Total Tasks | Done | In Progress | To Do | Blocked | % Complete | Notes
Frontend & UI | 7 | 2 | 2 | 3 | 0 | 28.57%
AI & NLP (LLM) | 6 | 1 | 2 | 3 | 0 | 16.67%
Maps & Places API | 4 | 0 | 0 | 4 | 0 | 0%
Database & Auth | 5 | 0 | 0 | 5 | 0 | 0%
Weather & Reviews API | 4 | 0 | 0 | 4 | 0 | 0%
Hosting & DevOps | 3 | 0 | 0 | 3 | 0 | 0%
Testing & QA | 3 | 0 | 0 | 3 | 0 | 0%
Documentation | 2 | 0 | 0 | 2 | 0 | 0%

## 🗂 Feature Tracker
🗂 Feature & Task Tracker
# | Feature / Task | Module | Status | Priority | Start Date | Target Date | Actual Done | Effort (hrs) | Notes | Assignee | Last Updated
1 | Set up Next.js project with App Router | Frontend & UI | Done | High |  |  |  | 4 |  | You
2 | Configure Tailwind CSS | Frontend & UI | Done | High |  |  |  | 2 |  | You
3 | Add Framer Motion animations | Frontend & UI | In Progress | Medium |  |  |  | 6 |  | You
4 | Build trip input / prompt UI | Frontend & UI | In Progress | High |  |  |  | 8 |  | You
5 | Build itinerary display UI | Frontend & UI | To Do | High |  |  |  | 10 |  | You
6 | Implement Zustand state management | Frontend & UI | To Do | Medium |  |  |  | 4 |  | You
7 | Responsive mobile layout | Frontend & UI | To Do | Medium |  |  |  | 6 |  | You
8 | Integrate OpenAI / Claude API | AI & NLP (LLM) | In Progress | High |  |  |  | 10 |  | You
9 | Set up Vercel AI SDK streaming | AI & NLP (LLM) | To Do | High |  |  |  | 6 |  | You
10 | Design JSON schema for itinerary | AI & NLP (LLM) | Done | High |  |  |  | 3 |  | You
11 | Craft system prompt for itinerary gen | AI & NLP (LLM) | In Progress | High |  |  |  | 5 |  | You
12 | Build 'Chat with itinerary' feature | AI & NLP (LLM) | To Do | High |  |  |  | 12 |  | You
13 | AI tool calling for weather/maps | AI & NLP (LLM) | To Do | Medium |  |  |  | 8 |  | You
14 | Integrate Google Places API | Maps & Places API | To Do | High |  |  |  | 6 |  | You
15 | Set up Mapbox GL JS map display | Maps & Places API | To Do | High |  |  |  | 8 |  | You
16 | Route optimization between stops | Maps & Places API | To Do | Medium |  |  |  | 8 |  | You
17 | Display place photos & ratings | Maps & Places API | To Do | Medium |  |  |  | 4 |  | You
18 | Set up PostgreSQL (Supabase/Neon) | Database & Auth | To Do | High |  |  |  | 4 |  | You
19 | Configure Prisma/Drizzle ORM | Database & Auth | To Do | High |  |  |  | 4 |  | You
20 | Implement Clerk / NextAuth login | Database & Auth | To Do | High |  |  |  | 5 |  | You
21 | Save & load itineraries for users | Database & Auth | To Do | High |  |  |  | 8 |  | You
22 | User profile page | Database & Auth | To Do | Low |  |  |  | 5 |  | You
23 | Integrate WeatherAPI.com | Weather & Reviews API | To Do | Medium |  |  |  | 4 |  | You
24 | Feed weather data into AI prompt | Weather & Reviews API | To Do | Medium |  |  |  | 3 |  | You
25 | Integrate TripAdvisor / Yelp reviews | Weather & Reviews API | To Do | Low |  |  |  | 5 |  | You
26 | AI review summarization | Weather & Reviews API | To Do | Low |  |  |  | 4 |  | You
27 | Deploy to Vercel | Hosting & DevOps | To Do | High |  |  |  | 2 |  | You
28 | Set up CI/CD pipeline | Hosting & DevOps | To Do | Medium |  |  |  | 3 |  | You
29 | Configure env variables & secrets | Hosting & DevOps | To Do | High |  |  |  | 2 |  | You
30 | Write unit tests for API routes | Testing & QA | To Do | Medium |  |  |  | 6 |  | You
31 | End-to-end testing (Playwright/Cypress) | Testing & QA | To Do | Medium |  |  |  | 8 |  | You
32 | API error handling & edge cases | Testing & QA | To Do | High |  |  |  | 5 |  | You
33 | Write README | Documentation | To Do | Low |  |  |  | 2 |  | You
34 | API docs / usage guide | Documentation | To Do | Low |  |  |  | 3 |  | You

## 📅 Sprint Log
📅 Weekly Sprint Log
Sprint # | Week Start | Week End | Goals / Tasks Planned | Tasks Completed | Blockers | Outcome | Notes
1
2
3
4
5
6
7
8
9
10
11
12

## 🐛 Bugs & Issues
🐛 Bug & Issue Tracker
# | Title | Module | Severity | Status | Reported Date | Steps to Reproduce | Expected | Actual | Resolution / Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## 🔗 Resources
🔗 Tech Stack & Resources
Category | Tool / Service | Purpose | Docs / Link | Notes
Frontend | Next.js | App framework | https://nextjs.org/docs | Use App Router
Frontend | Tailwind CSS | Styling | https://tailwindcss.com/docs
Frontend | Framer Motion | Animations | https://www.framer.com/motion/ | Premium feel micro-animations
Frontend | Zustand | State management | https://zustand-demo.pmnd.rs/
AI / LLM | OpenAI GPT-4o | Main LLM | https://platform.openai.com/docs | Or Claude 3.5 Sonnet
AI / LLM | Anthropic Claude | Alternative LLM | https://docs.anthropic.com | claude-3-5-sonnet
AI / LLM | Vercel AI SDK | Streaming AI in Next.js | https://sdk.vercel.ai/docs | Handles tool calling too
Maps | Google Places API | Places data & photos | https://developers.google.com/maps/documentation/places | Most comprehensive DB
Maps | Mapbox GL JS | Map display | https://docs.mapbox.com/mapbox-gl-js/ | Custom map styles
Maps | Google Routes API | Route optimization | https://developers.google.com/maps/documentation/routes | Travel time between stops
Database | Supabase | PostgreSQL hosting | https://supabase.com/docs | Free tier available
Database | Prisma ORM | DB queries (TypeScript) | https://www.prisma.io/docs
Auth | Clerk | User authentication | https://clerk.com/docs | Easy Google/Apple login
External APIs | WeatherAPI.com | Weather data | https://www.weatherapi.com/docs/ | Feed into AI prompt
External APIs | TripAdvisor API | Reviews | https://tripadvisor-content-api.readme.io/
External APIs | Yelp Fusion API | Reviews (alt) | https://docs.developer.yelp.com/
Hosting | Vercel | Deployment | https://vercel.com/docs | Auto scales with Next.js